## Checklist
Opening a New Property — IT Setup Checklist
From 'IT in Hospitality — A Practical Guide for Owners, Managers, and IT Teams' by Mark Townsend — resort-manager.com
How to use: work through the phases in the sequence given — each phase depends on the one before it. Choose ✓ in the Done? column as each item is completed and note the date or owner. Yellow cells are the ones to fill in.
Item | Done? | Date / Owner / Notes
Phase 1 — Before any equipment arrives
Internet service ordered, with an installation date confirmed in writing
A second connection technology identified for failover, even if not yet installed
PMS vendor selected and contract signed, including a confirmed go-live date
Payment processor / merchant account application submitted (approval can take weeks)
Domain name and business email registered
Comms room or cupboard identified, with power and ventilation confirmed
Phase 2 — Infrastructure
Router/firewall installed and configured with guest/operational separation
Network cabling run and labelled at both ends
Access points installed and positioned per a site survey, not guesswork
UPS installed on core network equipment, tested under load
Wi-Fi tested from every guest room and public area
Phase 3 — Core systems
PMS configured: room types, rate plans, tax settings, folio templates
Payment terminal(s) installed and test transactions processed and refunded
Booking engine connected to the property website
Channel manager connected to at least the first two OTAs, with a live test booking made and cancelled
Front desk hardware in place: terminal, card reader, key encoder
Phase 4 — Before opening
Staff trained on the PMS and payment workflow
Backup configured and one full restoration tested
Incident contact sheet completed and printed at the front desk
Documentation started: one-page systems summary
Emergency manual process (paper check-in, phone payment fallback) written and accessible
Phase 5 — First 30 days
Daily reconciliation habit established
Guest Wi-Fi tested for genuine isolation from operational systems
First backup restoration re-confirmed after real data has accumulated
Vendor contacts and renewal dates logged